ATLANTICUS

ADA Web Structural Migration & Qualification Plan

Capability-first consolidation before continuing KPI Configuration and remaining Managers

Document status APPROVED DESIGN BASELINE FOR MIGRATION. This document freezes the migration intent, sequencing, ownership rules, and qualification gates. It does not authorize broad functional redesign during the move.

| Project | Ecosystem Atlanticus / ADA Web |
| --- | --- |
| Baseline | Tools Configuration R8.4.5-r2 — CLOSED / GREEN |
| Primary objective | Reduce micro-packaging, restore domain-first ownership, preserve contracts and behavior |
| Implementation runtime | Python 3.14.2 + UV |
| Date | 2026-09-09 |

# 1. Purpose and migration boundary

This migration is a structural consolidation of ADA Web. Its purpose is to make the repository cleaner, easier to navigate, cheaper to maintain, and more scalable before continuing KPI Configuration and the remaining administrative Managers.

The migration must preserve every contract and behavior already qualified as GREEN. It is not a functional rewrite of Tools, Components, Content State, Inspection, Operational State, Time Status, or other existing capabilities.

Non-negotiable migration principle Move ownership and package boundaries without changing the semantics of already validated contracts. Functional changes are isolated and explicitly agreed; the only planned functional extension in this migration is the Branding variant capability described in Section 8.

## 1.1 Why the migration is required now

ADA Web currently mixes business/domain capabilities with technical implementation fragments at the same directory level.

Several responsibilities became separate UV projects and wheels even when they have no meaningful independent lifecycle.

The current shape creates version drift, repeated pyproject/lock/test/mirror maintenance, and longer dependency chains.

Continuing KPI Manager on top of the current shape would replicate the same fragmentation into future Managers.

The canonical Atlanticus Users and Navigation capabilities already demonstrate a cleaner pattern: domain capability first, configuration lifecycle and Web editor inside the same configuration package where justified.

## 1.2 Frozen baseline

Tools Configuration is the migration baseline. R8.4.5-r2 is CLOSED / GREEN, including stable identities, Process scope inheritance/override, Integrated Operations scope rules, partial inspection, serialized contract, tests, mirrors, CSS tokens, and repository gates.

All migration increments must preserve this behavior before the next increment begins.

# 2. Architectural rule to freeze

Atlanticus packaging rule The repository is organized first by capability/domain. Internal folders express responsibilities. A new wheel exists only when a real dependency, reuse, technology, or independent-versioning boundary justifies it.

domain != wheel
folder != wheel
module != wheel

Create a new wheel only when at least one of these is true:
- independently consumable contract
- dependency isolation is materially required
- independent reuse exists
- independent release/version lifecycle exists
- technology/infrastructure boundary must be enforced
- dependency direction must be protected

## 2.1 What this rule prevents

| Anti-pattern | Result | Migration response |
| --- | --- | --- |
| One responsibility = one wheel | Micro-packaging, lock/version drift, noisy dependency graph | Consolidate as internal module/subpackage |
| Generic configuration bucket | Domain ownership becomes unclear | Move configuration under owning capability |
| Generic UI bucket for domain-specific UI | Presentation detached from its domain | Return UI to physical capability |
| Host Manager owns feature logic | Manager becomes a monolith | Feature owns its configuration Web module; host only composes |

# 3. Target top-level ADA Web shape

scopes/ada/web/
├── application/
├── alarms/
├── branding/
├── components/
├── content-state/
├── inspection/
├── kpis/
├── operational/
├── shell/
├── time-status/
├── tools/
└── ui/
    └── only truly cross-domain visual primitives

The current generic `scopes/ada/web/configuration/` directory is expected to disappear as a broad ownership bucket. Configuration belongs to the domain it configures.

## 3.1 Ownership model

| Capability | Owns | Does not own |
| --- | --- | --- |
| tools | Tool contract, source participation, configuration lifecycle, Tool editor | KPI configuration, component runtime payload |
| kpis | KPI definitions and KPI administrative configuration | Tool identity generation |
| components | Component Store, delivery/hydration, structural render binding | Tool configuration lifecycle |
| content-state | Pure content state contracts/policies and dependency resolution | Time Status presentation |
| inspection | Inspection contracts, runtime, providers, surface/preview/resilience | Manager configuration |
| operational | Operational coordination/state | Domain-specific UI assets |
| time-status | Time Status state/adapters/presentation | Generic UI primitives |
| branding | Branding configuration, variant resolution, branding assets and presentation | Tool/KPI lifecycle |
| ui | Only generic visual primitives usable across domains | Domain-specific features |

# 4. Migration map: current → target

| Current route/package | Target owner | Target shape | Initial wheel decision |
| --- | --- | --- | --- |
| configuration/tools | tools | tools/core | Keep as core Tool wheel |
| configuration/tool-sources | tools | tools/core/source_* | Merge into Tool core |
| configuration/tools-lifecycle | tools | tools/configuration | Merge |
| configuration/tool-editor | tools | tools/configuration/web | Merge; Web optional dependency |
| configuration/kpi-definition | kpis | kpis/definition | Preserve capability boundary |
| configuration/kpi-configuration | kpis | kpis/configuration | Preserve one configuration wheel |
| component-store | components | components/store | Merge into ada-web-components |
| component-delivery | components | components/delivery | Merge into ada-web-components |
| operational-render-binding | components | components/render_binding | Merge unless audit finds a hard boundary |
| content-state/core | content-state | content-state/contracts + policies | Merge |
| content-state/dependency-resolver | content-state | content-state/dependency_resolver | Merge |
| inspection/* | inspection | inspection internal modules | Strong consolidation; likely one wheel |
| operational-state | operational | operational/state | Likely justified independent wheel |
| runtime-experience | TBD | Audit for Atlanticus promotion vs ADA ownership | No move until classification |
| time-status/store-adapter | time-status | time-status/store_adapter | Merge with Time Status capability |
| ui/time-status | time-status | time-status/web | Move to domain |
| configuration/branding + ui/branding | branding | branding config + resolver + web + resources | Merge into one capability wheel |

# 5. Detailed migration strategy by capability

## 5.1 Tools

tools/
├── core/
│   ├── identity
│   ├── models
│   ├── structure
│   ├── source_consumption
│   ├── operational_participation
│   └── validation
└── configuration/
    ├── bundle
    ├── contracts
    ├── source
    ├── lifecycle
    ├── projection
    ├── services
    ├── adapters/
    ├── web/
    └── resources/

Tool identity and structure remain canonical and behaviorally unchanged.

`tool-sources` becomes part of Tool core because those contracts describe Tool source consumption/participation.

`tools-lifecycle` moves into `tools/configuration`.

`tool-editor` moves into `tools/configuration/web`.

Web dependencies should be optional where the package can be consumed headlessly.

The ADA Configuration Manager remains a host/composer only.

## 5.2 Components

components/
├── store/
├── delivery/
└── render_binding/

Component Store, Component Delivery, and Operational Render Binding form one cohesive capability chain around the same Tool/Component identities. The initial target is a single `ada-web-components` wheel with internal modules.

Critical contract No new store_id, delivery_id, collector_target_id, destination_id, or render_id is introduced for the same semantic component. Tool → component identity remains anchored in tool_key/component_key.

## 5.3 Content State

content-state/
├── contracts.py
├── models.py
├── policies.py
└── dependency_resolver.py

The dependency resolver remains a pure responsibility but no longer requires a separate release unit unless the migration audit proves independent reuse.

## 5.4 Inspection

inspection/
├── core/
├── api/
├── providers/
├── runtime/
├── preview/
├── surface/
└── resilience/
    ├── empty_definition.py
    ├── interval.py
    └── portability.py

Inspection is the strongest consolidation candidate. The physical modules remain explicit, but separate pyproject/lock/version boundaries are removed where no independent package contract is required.

## 5.5 Operational State

Operational State remains a likely independent coordination capability because it composes multiple domains (Content State, Tool source participation, Time Status and UI state). It should move under `operational/state` without being merged blindly into any one input domain.

## 5.6 Runtime Experience

| Finding | Action |
| --- | --- |
| Fully generic browser/runtime behavior | Promote to Atlanticus Web framework/capability |
| ADA-specific behavior | Keep under ADA |
| Mixed | Split generic part from ADA-specific adapter/composition |

## 5.7 Time Status

time-status/
├── core/ or models/
├── store_adapter/
├── web/
└── resources/

The store adapter and the Time Status UI belong to the same domain unless a concrete cross-domain UI reuse case proves otherwise.

## 5.8 UI ownership cleanup

The `ui/` directory is not removed wholesale. Every child is classified according to semantic ownership.

| Question | Decision |
| --- | --- |
| Does the component carry domain semantics? | Move it into that physical domain/capability |
| Is it a generic visual primitive? | Keep it under `ui/` |
| Is it generic enough for Atlanticus, not ADA? | Consider promotion to Atlanticus Web |
| Is ownership unclear? | Do not move until dependency/consumer audit resolves it |

# 6. Migration sequence

The migration is executed incrementally. Every increment leaves the repository installable and testable. No long-lived compatibility layer is kept unless a real external consumer requires it.

| Increment | Scope | Primary outcome |
| --- | --- | --- |
| W-ARCH-001 | Branding consolidation | One Branding capability; current variants preserved; variant-to-assets resolver added |
| W-ARCH-002 | Tools domain consolidation | Tools core + configuration; remove tools-lifecycle/tool-editor/tool-sources wheels |
| W-ARCH-003 | Components consolidation | Store + Delivery + Render Binding under Components |
| W-ARCH-004 | Content State consolidation | Core + resolver become one capability package |
| W-ARCH-005 | Time Status consolidation | Adapter + domain-specific UI reunited |
| W-ARCH-006 | UI ownership cleanup | Move domain UI out of generic ui/; retain only primitives |
| W-ARCH-007 | Inspection consolidation | Reduce micro-packages while preserving internal modules |
| W-ARCH-008 | Operational organization | Operational State placed under coherent domain tree |
| W-ARCH-009 | Runtime Experience classification | Promote/keep/split based on actual semantics |
| W-ARCH-010 | KPI physical landing | kpis/definition + kpis/configuration ready for KPI Manager |
| W-ARCH-011 | Repository full qualification | All consumers, tests, locks, mirrors and runtime smoke GREEN |

## 6.1 Increment contract

Verify baseline HEAD and clean working tree.

Map current files, imports, package names, dependency declarations, tests and mirrors.

Move code with no semantic rewrite.

Update all in-repository consumers in the same increment.

Remove the old wheel/package boundary once no consumer remains.

Run package-local gates.

Run consumer gates.

Run repository-level qualification.

Only then freeze the increment and proceed.

# 7. Qualification and testing strategy

Because this work is a structural migration, success is not measured only by unit tests. The qualification must prove source equivalence, dependency integrity, application startup, runtime behavior, Manager behavior and absence of stale imports.

## 7.1 Gate layers

| Layer | Required checks |
| --- | --- |
| Source quality | ruff format, ruff check, format --check, Python 3.14.2 |
| Unit | pytest for migrated package and every directly affected consumer |
| Packaging | uv sync --frozen, uv lock --check, build/install/import smoke where relevant |
| Mirrors | commented mirror validation for every moved package |
| Repository | CSS token validation, git diff --check, stale path/import search |
| Contracts | before/after serialization compatibility for frozen documents |
| Runtime | application composition/startup, import graph, projection/read path smoke |
| Visual | targeted UI smoke for Manager/operational surfaces touched by moves |

## 7.2 Contract regression matrix

| Contract area | Must remain true |
| --- | --- |
| Tool identity | Rename/scope edits preserve tool_key |
| Component identity | Rename/scope edits preserve component_key |
| Subcomponent identity | Rename preserves subcomponent_key |
| Process scope | Root scope is required default; component override remains optional/canonicalized |
| Integrated scope | Each component explicit mine/plant; mine-only, plant-only and mixed topologies remain valid |
| Tool projection | Downstream destination/component consumers see the same semantic keys |
| Component store | Store snapshots still address exact tool_key/component_key |
| Component delivery | Delivery does not translate semantic identity |
| KPI destination bridge | Component destination_key remains component_key |
| Time Status | Existing operational timestamps/state/rendering remain equivalent |
| Inspection | Public inspection contracts and runtime behavior remain equivalent |
| Manager | Host still composes independent modules and does not absorb domain logic |

## 7.3 Stale-reference checks

Search for old package names after each increment.

Search for old physical paths in pyproject.toml and UV source declarations.

Search for tests importing removed namespaces.

Search for application composition still referencing old wheels.

Search for mirror paths excluded from validation.

Search for lock files/packages that became orphaned.

## 7.4 No silent compatibility drift

Migration safety Do not add hidden aliases, duplicate IDs, automatic key translation, or temporary semantic adapters unless an external consumer genuinely requires them. The preferred migration is atomic inside the repository: update consumers, remove old boundary, qualify.

# 8. Branding consolidation and variant capability

Branding is a transversal ADA Web capability and should become its own domain rather than remain split between `configuration/branding` and `ui/branding`.

branding/
├── models.py
├── resolver.py
├── web/
│   ├── models.py
│   ├── presentation.py
│   └── module.py
└── resources/
    ├── css/
    └── img/

## 8.1 Persisted contract

The persisted configuration stays small and stable. Existing value `original` is retained for compatibility and presented in the UI as “Normal”.

| Persisted value | Display label |
| --- | --- |
| original | Normal |
| mining_month | Mes de la Minería |
| fiestas_patrias | Fiestas Patrias |
| christmas | Navidad |
| new_year | Año Nuevo |

## 8.2 Asset resolution

BrandingConfiguration(variant)
        │
        ▼
BrandingAssetResolver
        │
        ├── primary_logo
        ├── secondary_logo
        ├── partner_logo
        └── presentation metadata

Tool/KPI configuration stores the semantic variant only. Physical asset paths remain owned by Branding, so logo files can be replaced without rewriting configuration documents.

## 8.3 Branding acceptance tests

Existing `original` documents load without migration.

Every declared variant resolves to a complete and valid asset set.

Unknown/invalid variants fail through the existing validation contract.

Normal/Fiestas Patrias/etc. can be selected without changing Tool identity.

Brand rendering falls back safely to Normal only where the contract explicitly permits it; invalid persisted configuration must not be silently accepted.

Manager and operational surfaces resolve the selected variant consistently.

# 9. Risk register and controls

| Risk | Impact | Control |
| --- | --- | --- |
| Import graph breaks during moves | High | Atomic consumer updates + package import smoke + stale namespace search |
| Version drift between former micro-wheels | High | Consolidate release unit and lock dependencies together |
| Behavior changes hidden in refactor | High | No semantic rewrites; contract regression tests before/after |
| UI regressions from asset/path moves | Medium | CSS token gate + targeted visual smoke |
| Mirror divergence | Medium | Mirror migration in same change + validate_mirrors |
| Orphaned pyproject/uv.lock files | Medium | Repository tree audit after each consolidation |
| Over-consolidation removes real boundary | Medium | Pre-move dependency/consumer audit; keep wheel when justified |
| Long-lived compatibility layer becomes permanent | Medium | Prefer atomic migration; any temporary alias gets explicit removal gate |
| KPI work starts before structural baseline stabilizes | High | KPI Manager remains blocked until W-ARCH-011 GREEN |

# 10. Change-control rules during migration

Do not redesign closed Tools behavior during physical migration.

Do not introduce new IDs or translation layers for existing semantic identities.

Do not move generic Atlanticus code into ADA merely for convenience.

Do not promote ADA-specific semantics into Atlanticus framework.

Do not create a new wheel simply to mirror a folder structure.

Do not combine independent domains solely to reduce wheel count.

Any functional change outside Branding variants requires explicit discussion and a separate acceptance criterion.

Every increment must include production code, tests, and commented mirror changes together.

# 11. Final repository qualification (W-ARCH-011)

| Gate | Expected final state |
| --- | --- |
| Repository tree | Domain-first ownership; generic configuration bucket removed or reduced to justified transversal capability only |
| Wheels | Only justified independent packages remain |
| Imports | No stale old namespaces or source paths |
| Locks | All active packages frozen and consistent |
| Mirrors | Validated |
| CSS tokens | Validated |
| Unit/consumer tests | GREEN |
| Application startup | GREEN |
| Manager shell | GREEN |
| Tools configuration | Behavior-equivalent to R8.4.5-r2 |
| Operational surfaces | GREEN |
| Branding variants | GREEN |
| KPI prerequisites | Tool projection/component destination flow ready |

Migration closure condition Only after W-ARCH-011 is GREEN may KPI Configuration implementation resume. At that point the remaining Managers must follow the new capability-first package rule.

# 12. Handoff after structural migration

Once the migration is closed, KPI Configuration becomes the first configuration capability implemented entirely on the cleaned structure.

kpis/
├── definition/
└── configuration/
    ├── domain/lifecycle/services
    ├── projection/source
    ├── web/
    └── resources/

KPI Configuration will then implement the previously agreed behavior: readable KPI names with stable kpi_key identity, projected Tool components as selectable destinations, independent Latest/Time Series flags, conditional series hours, valid “neither” delivery state, modal Add/Edit, deletion with confirmation, filter/search, and pagination from the first release (10 rows default with adjustable page size).

The ADA Configuration Manager will only compose the KPI configuration module, following the same independence rule used by Users, Navigation, Tools and all future administrative capabilities.

# 13. Formal checkpoint

STRUCTURAL MIGRATION DESIGN
STATUS: FROZEN FOR IMPLEMENTATION

Baseline:
Tools Configuration R8.4.5-r2 — CLOSED / GREEN

Migration objective:
Capability-first ADA Web
Reduced wheel count
Preserved contracts
No hidden semantic rewrites
Repository fully requalified before KPI Manager

Next executable increment:
W-ARCH-001 — Branding Consolidation